## Gantt
Project Gantt
Organization: BGU |  | Last Update: 11/6/23
Project Name: MolOpt
| November |  | December |  | January |  |  | February | March |  | April |  |  | May |  | June
| Gathering up + Planning and designing |  | Adding all the | Adding validation | Adding multiple | Adding Cancel / |  | Integrating Backend and Frontend | Adding files | Adding multiple | Adding Cancel / | DDOS limitations |  | Adding multiple runs /
Frontend Team |  |  | relevant / needed | of user input | choice functionality | Update choice for |  |  | validation | choice functionality | Update choice for |  |  | running queue functionality
Backend Team |  |  | UI pages | (no files | in the system | Algorithms runs |  |  |  | in the system | Algorithms runs
All Teams |  |  |  | valiadtion yet) | [8 empty] | Finalize User/Runs |  | Upload / Deploy
Done Tasks | [9 empty] | Finalize database |  |  | Managements |  | to University's
Others |  |  | Adding files management & upload |  | Adding full notifications |  |  |  |  | & connecting it to |  |  | (Front & Backend) |  | servers
Future Tasks |  |  | system for the existing algorithms |  | system to the app |  |  |  |  | the app
|  |  | Integrating the server to the current UI |  | Creating all user | Creating database |  |  | Adding Security & Robutness |  |  | Optimizing the app performance
Note: |  |  |  |  | management logic | & connecting it to
Each square in the schedule | [5 empty] | the app
presents a week in the month | [13 empty] | Start testing the full system
Final testing and finishing toches
Tests Period (University Tests)
Amit Peled, Daniel Piro, Nofar Rozenberg & Shahar Alon